LEGACY OF THE REALM

PARTNERSHIPS & ANALYTICS

Sponsor & Partnership Database | Post-Event Analytics Framework

The Final Companion Document to the Master Blueprint v2.0

Document Date: March 2026

Version: 1.0

Part I: Partnerships — 14 partner categories, 24-field pipeline tracker, 13-step outreach priority, immersion protection policy, partnership value model

Part II: Analytics — Data collection timeline, 40+ KPIs across 4 categories, post-event survey template, year-over-year comparison framework, analytics report template, continuous improvement cycle

DOCUMENT 10 OF 10 This completes the Legacy of the Realm operational library.

— CONFIDENTIAL —

# Table of Contents

# Part I: Sponsor & Partnership Database

Legacy of the Realm cannot exist in isolation. It needs local farms for food, breweries for ale, equestrian centers for horses, artisans for props, tourism boards for promotion, and potentially corporate sponsors for capital. This database tracks every potential and active partnership from first contact through multi-year relationship.

Principle: partnerships should SERVE THE IMMERSION, not break it. A brewery partner who brews ‘Realm Ale’ adds authenticity. A corporate sponsor who wants a branded banner in Market Row destroys it. The filter is always: does this make the Realm more real, or less?

## 1A. Partnership Categories

| Category | What They Provide | What We Offer Them | Immersion Fit | Priority | Examples |
| --- | --- | --- | --- | --- | --- |
| Local Brewery / Meadmaker | Festival-branded ale, mead, cider. Period-style beverages. Keg supply. Possible on-site brewing demo. | Exclusive pouring rights (or primary). Brand mention in materials. In-world identity (‘Official Ale of the Realm’). Volume sales. | VERY HIGH — period beverages are core immersion. The brewer CAN be an in-world character. | CRITICAL (Y0) | Craft breweries within 50km of Chazeuil. Meadmakers. Cideries. |
| Local Farm(s) | Eggs, vegetables, fruit, herbs, dairy, meat (some). Possibly livestock for display (chickens, goats). | Reliable bulk orders for 8+ days. ‘Farm-to-Realm’ marketing. In-world credit (‘Supplied by Ferme de [name]’). | VERY HIGH — local farm produce is more authentic than supermarket. Livestock transforms atmosphere. | HIGH (Y0) | Farms within 30km. AMAP networks. Local marché producers. |
| Local Boulangerie / Baker | Daily bread supply (100+ loaves/day). Possibly on-site bread oven collaboration. | Volume daily order for 8–10 days. ‘Baker to the Realm’ marketing. | VERY HIGH — fresh bread is the single most immersive food smell. | HIGH (Y0) | Boulangeries artisanales within 20km. |
| Local Boucherie / Charcutier | Meat supply: beef, pork, lamb, sausages, charcuterie. Quality local sourcing. | Volume orders. Reliable repeat business. | HIGH — quality meat improves feast dramatically. | HIGH (Y0) | Boucheries, charcutiers within 30km. |
| Equestrian Center / Riding School | Horses (2–4), handlers, equipment, possibly cart/wagon. Mounted demonstrations. | Fee for service. Promotion to their audience. Cross-marketing. | VERY HIGH — horses transform the Realm from festival to living world. | MEDIUM (Y1+) | Local écuries, centres équestres. Percheron breeders (central France specialty). |
| Falconry Center | Birds of prey, licensed handlers, demonstration equipment. | Fee for service. Premium attraction billing. Promotion. | VERY HIGH — falconry is peak medieval prestige. Magnetic crowd draw. | LOW (Y2+) | Licensed falconry centers within 100km. Regional bird sanctuaries. |
| Tourism Board / Office de Tourisme | Regional promotion, visitor guides listing, tourism website feature, possible grant funding. | Cultural event in the region. Tourism traffic. Heritage valorization narrative. | NEUTRAL — they promote us, they don’t appear in the Realm. | MEDIUM (Y1) | Office de Tourisme local, Comité Départemental du Tourisme, Atout France (national). |
| Regional Cultural Authority / DRAC | Potential grant funding (aide à la création, patrimoine vivant). Legitimacy endorsement. | Cultural valorization of heritage site. Educational programming. Visitor engagement with patrimoine. | POSITIVE — DRAC endorsement strengthens ABF relationship and public credibility. | MEDIUM (Y0–Y1) | DRAC Auvergne-Rhône-Alpes (or relevant region). Fondation du Patrimoine. |
| Local Municipality / Mairie | Permits, road access, noise tolerance, local goodwill, possible in-kind support (waste collection, signage). | Economic activity in commune. Employment. Tourism. Cultural prestige. | NEUTRAL to POSITIVE — good Mairie relationship makes everything easier. | CRITICAL (Y0) | Mairie de Chazeuil + neighboring communes. |
| Media Partners | Press coverage, documentary interest, influencer content, photography. | Access, exclusive content, behind-the-scenes, interview opportunities, premiere footage. | VARIES — editorial coverage is great. Sponsored content must be invisible. | MEDIUM (Y0–Y1) | LARP/medieval niche press. Travel press. Documentary producers. Select influencers (2–3 max, curated). |
| Corporate Sponsors | Cash investment. Equipment loans. Service provision (e.g., portable toilet company, generator rental at discount). | Logo placement (NEVER in guest-visible areas — website, printed materials, press releases only). Hospitality packages. VIP access. | DANGEROUS if mishandled. Corporate branding inside the Realm destroys immersion. Must be kept strictly off-stage. | LOW until Y2+ | Event industry suppliers. Regional businesses. Cultural foundations. |
| Artisan Partnerships | Skilled craftspeople who operate guild workshops in exchange for free access + sales rights. | Free ticket + stall/workshop space + in-world status (Guild Master). They bring skill and authenticity. | VERY HIGH — real artisans ARE the immersion. | HIGH (Y0) | Blacksmiths, leatherworkers, weavers, potters, woodworkers. Reenactment artisan community. |
| HEMA / Martial Arts Clubs | Combat trainers, tournament marshals, safety expertise, experienced fighters. | Free tickets for members. Training space. Tournament participation. Community cross-promotion. | HIGH — trained fighters improve combat quality and safety. | HIGH (Y0–Y1) | Local HEMA clubs. SCA chapters. Reenactment combat groups. |
| Music Ensembles / Folk Groups | Performers, instruments, repertoire, atmosphere. | Free tickets + meals + performance fees (for professionals). Stage time. Audience. | VERY HIGH — live period music defines atmosphere. | HIGH (Y0) | Medieval/Renaissance music ensembles. Folk music collectives. Conservatory early music departments. |

## 1B. Partnership Pipeline Tracker (Airtable Schema)

| Field | Type | Description |
| --- | --- | --- |
| partner_id | Auto-number | Unique identifier |
| partner_name | Text | Organization or individual name |
| category | Single select | Brewery, Farm, Baker, Butcher, Equestrian, Falconry, Tourism, DRAC, Mairie, Media, Corporate, Artisan, HEMA, Music, Other |
| contact_name | Text | Primary contact person |
| contact_email | Email |  |
| contact_phone | Phone |  |
| website | URL |  |
| location | Text | City/commune + distance from Chazeuil |
| pipeline_stage | Single select | Identified, Contacted, Meeting Scheduled, Proposal Sent, Negotiating, Agreed, Active, Dormant, Declined |
| relationship_owner | Linked record → Staff | Who manages this relationship |
| first_contact_date | Date | When we first reached out |
| last_contact_date | Date | Most recent communication |
| next_action | Text | What’s the next step? ‘Send proposal by April 15.’ |
| next_action_date | Date | Deadline for next step |
| what_they_provide | Long text | What we want from them |
| what_we_offer | Long text | What we offer in return |
| agreement_type | Single select | Barter (exchange of value), Fee-for-service (we pay them), Sponsorship (they pay us), Hybrid, In-kind, None yet |
| estimated_value | Currency (EUR) | Estimated annual value of partnership (cash or in-kind equivalent) |
| contract_signed | Checkbox | Formal agreement in place |
| contract_document | Attachment | Signed contract/agreement PDF |
| event_years_active | Text | Which years they’ve been active: ‘Y0, Y1’ |
| satisfaction_rating | Number (1–5) | Our satisfaction with this partner: 1=poor, 5=excellent |
| notes | Long text | Relationship history, key conversations, issues, opportunities |
| immersion_impact | Single select | Enhances immersion, Neutral, Risks immersion |

## 1C. Partnership Outreach Priority Matrix

Who to contact first, in what order, and why.

| Priority | Category | When to Contact | Why This Order | Approach |
| --- | --- | --- | --- | --- |
| 1 | Mairie de Chazeuil | Month 1 (immediately) | Everything depends on local government goodwill. Permits, noise, roads, camping — the Mairie is gate zero. | Personal visit by founder. Formal letter of introduction. Emphasize cultural valorization, tourism, local employment. |
| 2 | Local brewery / meadmaker | Month 2–3 | Beverage is the single largest partnership by volume and revenue impact. Lead time for custom brewing is 6–12 weeks. | Visit in person. Bring the concept document. Propose ‘Realm Ale’ collaboration. Start with pilot-scale order. |
| 3 | Local farm(s) for food supply | Month 3–4 | Food supply must be locked in well before the event. Farms plan seasons ahead. | Visit farms. Explain volume and timing. Ask about delivery logistics. Start with one primary + one backup. |
| 4 | Local boulangerie | Month 3–4 | Daily bread requires a standing order relationship. Baker needs advance notice for volume. | Visit. Explain: 100 loaves/day for 8–10 days. Ask about wood-fired options. Negotiate bulk pricing. |
| 5 | Artisan guild masters | Month 4–6 | Real craftspeople need time to plan, prepare tools, and arrange time off work/life. | Attend reenactment events and craft fairs. Approach in person. Offer free ticket + workshop space. Sell the vision. |
| 6 | HEMA / martial arts clubs | Month 4–6 | Fighters need training coordination and safety planning. | Contact club leaders. Invite to pre-pilot. Offer group tickets at discount. Propose tournament collaboration. |
| 7 | Music ensembles / folk musicians | Month 4–6 | Musicians book seasons ahead. Best performers go first. | Contact early music societies, folk festival organizers. Offer performance residency (full event, free ticket + meals + small fee for professionals). |
| 8 | Local boucherie / charcutier | Month 5–6 | Meat supply needs less lead time than brewery but still requires advance ordering. | Visit. Explain volume. Negotiate 2-day delivery cycle during event. |
| 9 | Tourism board / Office de Tourisme | Month 6–8 | Tourism promotion has long lead times for print guides and website updates. | Formal letter + event summary + projected visitor numbers. Ask about listing and promotion support. |
| 10 | DRAC / cultural funding | Month 6–8 | Grant applications have specific windows. Research délais de dépôt. | Research available programs (patrimoine vivant, aide à la création culturelle). Prepare dossier emphasizing heritage valorization. |
| 11 | Media partners | Month 8–10 | Media engagement should happen AFTER you have content (pre-pilot footage) to show. | Press kit with pre-pilot footage. Invite 2–3 curated influencers/journalists to pilot. Editorial, not advertising. |
| 12 | Equestrian center | Month 8–12 (for Y1) | Horses are complex: insurance, handlers, logistics. Not for the pilot unless already established. | Visit local écuries. Propose partnership for Y1. Start with 2 horses + handlers for specific event days. |
| 13 | Corporate sponsors | Year 2+ | Do NOT seek corporate money before the event has proven itself. Sponsors need proof. | Approach only with documented attendance, media coverage, and audience demographics. Professional sponsorship deck. |

## 1D. Sponsorship Rules — Immersion Protection Policy

This policy protects the Realm from commercial contamination. It is NON-NEGOTIABLE.

| Rule | Detail | Exception |
| --- | --- | --- |
| NO corporate logos or branding visible anywhere in the guest experience | No banners, signs, stickers, screens, wearables, or any visual element bearing a corporate identity within any guest-facing zone of the Realm. | Backstage/logistics area only. Website sponsor page. Printed program (if one exists). Press releases. |
| NO product placement inside the Realm | No branded products, samples, or promotional materials distributed to participants during the event. | A brewery partner’s ale may be served under an IN-WORLD name (‘The Brewer’s Best’). The real brewery name appears only on the website/materials. |
| NO sponsor-driven programming | No sponsor-required events, activations, speeches, or any content shaped by a sponsor’s marketing goals. | A sponsor may be acknowledged at the Opening or Closing Ceremony with a brief ‘The Realm thanks [name] for their support’ — once, not repeated. |
| NO data sharing with sponsors | Participant personal data (emails, names, demographics) is NEVER shared with sponsors without explicit participant consent. | Anonymized aggregate data (total attendance, demographic summary) may be shared for sponsorship reporting. |
| Sponsor hospitality is IN-WORLD | Corporate guests of sponsors attend as participants, in costume, under realm rules. They do not receive branded VIP areas. | Sponsors may receive Noble-tier tickets at a discount. Their guests enter the Realm as nobles, not as ‘sponsored visitors.’ |
| The Sovereign has VETO power | The founder/Sovereign can reject any sponsorship that threatens immersion quality, regardless of financial value. | No exception. Money never overrides world integrity. |

## 1E. Partnership Value Model

| Partner Type | Estimated Annual Value (Y1) | Cost to Us | Net Value | Grows With Scale? |
| --- | --- | --- | --- | --- |
| Brewery (primary) | €3,000–5,000 (beverage supply at wholesale + custom brew) | €2,500–4,000 (product cost) | €500–1,000 margin + immersion value | YES — volume scales with attendance |
| Farm(s) (food supply) | €5,000–8,000 (produce at farm-gate prices) | €5,000–8,000 | Near break-even vs. wholesale + freshness + authenticity | YES |
| Boulangerie | €1,200–1,800 (bread supply) | €1,200–1,800 | Break-even + freshness + immersion | YES |
| Artisan guild masters (5–10) | €3,000–6,000 (skilled labor equivalent) | €2,500–5,000 (free tickets + space) | Net positive: we get skilled labor, they get a venue. Win-win. | YES — more artisans = richer world |
| Musicians (6–12) | €5,000–8,000 (performance value equivalent) | €2,500–5,500 (tickets + meals + fees) | Net positive: atmosphere transformation far exceeds cost | YES |
| Tourism board | €1,000–5,000 (promotion value) | €0 (our effort only) | Pure upside if they list and promote us | YES |
| DRAC / cultural grant | €2,000–10,000 (if grant obtained) | €0 + application effort | Pure upside | Possible but not guaranteed |
| Equestrian (Y1+) | €3,000–5,000 (prestige + premium experiences) | €3,000–5,000 (handler fees + logistics) | Break-even financially but HUGE immersion multiplier | Moderately |
| Corporate sponsor (Y2+) | €5,000–20,000 (cash or in-kind) | €0 (except hospitality) | Pure revenue if immersion rules are respected | YES |
| TOTAL PARTNERSHIP ECOSYSTEM (Y1) | €23,000–70,000 value | €17,000–35,000 cost | €6,000–35,000 net + immersion value |  |

# Part II: Post-Event Analytics Framework

What gets measured gets improved. This framework defines exactly what data to collect after each event, how to analyze it, what benchmarks to target, and how to compare year-over-year. It transforms ‘it felt good’ into ‘we know exactly what worked, what didn’t, and what to change.’

The Analytics Lead role is assigned to the Community & Marketing Director, with support from the Economy Director (financial data) and Immersion Director (content data). The post-event analytics report should be completed within 6 weeks of each event.

## 2A. Data Collection Timeline

| When | What to Collect | How | Who | Deadline |
| --- | --- | --- | --- | --- |
| During event (continuous) | Economy data: token transactions, daily velocity samples, treasury counts | Treasury daily log + Airtable transaction records | Economy Director + Treasury Clerks | Real-time (logged daily) |
| During event (continuous) | Quest completion data: which quests completed, by whom, time taken | Quest Lead logs in Airtable (Quest table: status field) | Quest Lead + Quest Runners | Real-time (logged on completion) |
| During event (continuous) | Reputation events: all rep changes logged | Warden/Guild Master entries in Airtable (Reputation Events table) | Wardens, Guild Masters, Immersion Director | Real-time |
| During event (continuous) | Safety incidents: all incidents logged in incident report forms | Paper forms at Medical Station + post-event digitization | Medical Lead + Safety Director | Paper real-time; digital within 48hrs post-event |
| During event (daily) | Attendance by zone: visual estimate of traffic levels by zone at 3 time points (morning, afternoon, evening) | Wardens report via radio; logged in daily ops summary | Warden Supervisor | Daily evening debrief |
| During event (daily) | Food service counts: meals served per service window | Kitchen tally counter or manual count | Head Cook | Post-service each meal |
| Event close (Monday) | Token redemption data: how many tokens redeemed, converted to credit, spent on merchandise, or abandoned | Treasury redemption desk log | Economy Director | Monday evening |
| Post-event Day +2–3 | Participant survey: satisfaction, return intent, NPS, qualitative feedback | Online survey (Google Forms, Typeform, or SurveyMonkey) emailed to all participants | Community Director | Survey sent Day +2. Open for 2 weeks. |
| Post-event Day +7–14 | Staff and volunteer debrief: structured feedback from all departments | Department-level debrief meetings (1 hour each) + written summary | Operations Director facilitates; each dept head submits written summary | All debriefs completed within 2 weeks |
| Post-event Day +14–28 | Financial reconciliation: actual revenue vs. budget, actual costs vs. budget, variance analysis | Finance spreadsheet + Airtable Budget table | Finance Lead / Economy Director | 4 weeks post-event |
| Post-event Day +28–42 | Full analytics report compiled and presented to core team | Written report with visualizations (charts, tables) | Community Director + Analytics Lead | 6 weeks post-event |

## 2B. KPI Dashboard — Master Metrics

These are the numbers that matter most. They are reported in the post-event analytics report and compared year-over-year.

### Attendance & Participation

| KPI | Definition | Data Source | Y0 Target | Y1 Target | Y3 Target | Red Flag If |
| --- | --- | --- | --- | --- | --- | --- |
| Total attendance | Unique participants checked in at Crown Gate | Registration check-in data | 150–250 | 400–500 | 700–800 | Below 70% of tickets sold |
| Show rate | Checked in / confirmed tickets | Registration vs. ticket sales | >85% | >90% | >95% | Below 80% (indicates pricing, logistics, or commitment problem) |
| Average stay duration | Nights stayed / total possible nights | Registration check-in/check-out | >90% stay full event | >95% | >98% | Below 85% (people leaving early = experience problem) |
| Class distribution | % of participants per class | Registration data | Close to planned ratio | Within 20% of target per class | Within 10% | Any single class >40% (homogeneity) or <5% (dead class) |
| New vs. returning | % first-time vs. returning participants | CRM events_attended field | 100% new (first event) | 60–70% new / 30–40% returning | 40–50% new / 50–60% returning | Returning drops below 30% at Y2+ (retention crisis) |

### Satisfaction & Sentiment

| KPI | Definition | Data Source | Y0 Target | Y1 Target | Y3 Target | Red Flag If |
| --- | --- | --- | --- | --- | --- | --- |
| Overall satisfaction (1–10) | Average survey score to ‘How would you rate your overall experience?’ | Post-event survey | 7.0+ | 7.5+ | 8.5+ | Below 6.5 |
| Net Promoter Score (NPS) | ‘Would you recommend this to a friend?’ (0–10). NPS = %Promoters(9–10) − %Detractors(0–6) | Post-event survey | +20 | +35 | +50 | Below 0 (more detractors than promoters) |
| Return intent | % answering ‘Definitely’ or ‘Probably’ returning | Post-event survey | 50%+ | 60%+ | 70%+ | Below 40% |
| Immersion rating (1–10) | ‘How immersive did the world feel?’ | Post-event survey | 7.0+ | 7.5+ | 8.5+ | Below 6.0 (immersion failure) |
| Food quality rating (1–10) | ‘How would you rate the food and drink?’ | Post-event survey | 6.5+ | 7.0+ | 8.0+ | Below 5.5 (food is fundamental) |
| Value for money (1–10) | ‘Did you feel the event was good value for the price?’ | Post-event survey | 6.5+ | 7.0+ | 8.0+ | Below 5.0 (pricing crisis) |
| Safety perception (1–10) | ‘Did you feel safe throughout the event?’ | Post-event survey | 8.0+ | 8.5+ | 9.0+ | Below 7.0 (safety perception crisis) |
| Top 3 positives | Open-text: ‘What were the best parts of your experience?’ | Post-event survey (coded thematically) | Identify themes | Track theme evolution | Track theme evolution | If negative themes dominate top mentions |
| Top 3 negatives | Open-text: ‘What would you most like improved?’ | Post-event survey (coded thematically) | Identify themes | Track whether Y0 issues resolved | New issues < recurring issues | Same complaints Y0→Y1→Y2 = failure to improve |

### Economic Performance

| KPI | Definition | Data Source | Y0 Target | Y1 Target | Y3 Target | Red Flag If |
| --- | --- | --- | --- | --- | --- | --- |
| Total revenue | All income: tickets + food + merchandise + token exchange + sponsorship | Finance records | Break-even | €300K–500K | €600K–900K | Below 60% of budget projection |
| Revenue per participant | Total revenue / total participants | Finance + registration | €200–400 (pilot pricing) | €700+ | €900+ | Below €500 at Y1 (underpriced or underserved) |
| Total costs | All expenses: staff, infrastructure, food, insurance, marketing, props, contingency | Finance records | < revenue | ~€230K | ~€400K | Exceeds revenue by >10% without explanation |
| Net margin | Revenue − costs | Finance records | ≥€0 (break-even) | €70K–100K | €150K–250K | Negative at Y1+ (unsustainable) |
| Token velocity (avg daily) | Total tokens transacted per day / total tokens in circulation | Treasury daily logs | Data collection (no target yet) | 0.3–0.5 (30–50% of supply moves daily) | Stable at 0.3–0.5 | Below 0.2 (stagnant economy) or above 0.7 (hyperactive / inflation risk) |
| Token redemption rate | Tokens redeemed for cash / total tokens distributed | Treasury redemption log | Data collection | <30% (most tokens stay in-world) | <25% | Above 40% (people extracting cash rather than reinvesting) |
| Food revenue vs. cost | Food token income vs. food procurement + operation cost | Kitchen + Treasury records | Data collection | Break-even to +10% | +5–15% | Food losing >10% = unsustainable |
| Ticket sell-through rate | Tickets sold / tickets available | Ticket platform | >60% | >75% | >85% | Below 50% (marketing or pricing problem) |
| Early bird conversion | Early bird tickets / total tickets | CRM data | N/A (first event) | >30% | >40% | Below 20% (insufficient return loyalty or poorly timed offer) |

### Operational Performance

| KPI | Definition | Data Source | Y0 Target | Y1 Target | Red Flag If |
| --- | --- | --- | --- | --- | --- |
| Safety incidents (total) | All logged incidents requiring medical attention or safety intervention | Incident report forms | <5 | <10 | >15 or any single serious injury |
| Quests completed | Total quests completed / total quests deployed | Quest table in Airtable | >50% completion rate | >65% | Below 40% (quests aren’t engaging or findable) |
| Titles granted | Total reputation titles awarded during the event | Reputation system | 10–20 | 30–60 | Below 10 at Y1 (system underused) |
| Settlements named | New persistent settlements established | Lore database | 0 (pilot) | 3–5 | 0 at Y1 (settlement system not working) |
| Guild charters granted | New guilds officially chartered | Scriptorium records | 1–2 | 3–5 | 0 at Y1 (guild system not engaging) |
| Staff satisfaction (1–10) | Average staff/volunteer survey score | Staff debrief survey | 7.0+ | 7.5+ | Below 6.0 (staff burnout or management failure) |
| Volunteer return intent | % of volunteers saying they’ll return to volunteer | Staff survey | 60%+ | 70%+ | Below 50% (volunteer model at risk) |
| Permit compliance | All required permits obtained and no regulatory issues during event | Legal/Permits tracker | 100% | 100% | Any permit violation or regulatory issue |
| Waste management | All waste removed. No environmental complaints. | Site Manager report | 100% | 100% | Any environmental complaint or uncleared waste |

## 2C. Post-Event Survey Template

This survey is sent to all participants 2–3 days after the event. It should take 8–10 minutes to complete. Keep it focused — long surveys get abandoned.

| # | Question | Type | Scale / Options | Required? | Purpose |
| --- | --- | --- | --- | --- | --- |
| 1 | How would you rate your overall experience at Legacy of the Realm? | Scale | 1–10 | YES | Primary satisfaction metric |
| 2 | How immersive did the world feel? | Scale | 1–10 | YES | Immersion quality metric |
| 3 | How would you rate the food and drink? | Scale | 1–10 | YES | Food quality metric |
| 4 | How would you rate the value for money? | Scale | 1–10 | YES | Pricing validation |
| 5 | Did you feel safe throughout the event? | Scale | 1–10 | YES | Safety perception |
| 6 | How likely are you to recommend Legacy of the Realm to a friend? | Scale | 0–10 (NPS format) | YES | Net Promoter Score |
| 7 | How likely are you to return next year? | Single select | Definitely / Probably / Maybe / Unlikely / Not returning | YES | Return intent |
| 8 | What class did you play? | Single select | [10 classes] | YES | Class-specific analysis |
| 9 | Was this your first time attending? | Single select | Yes / No (returning from Y…) | YES | New vs. returning segmentation |
| 10 | What were the 3 best parts of your experience? | Open text | Free text | YES | Positive theme identification |
| 11 | What 3 things would you most like improved? | Open text | Free text | YES | Negative theme identification / improvement priorities |
| 12 | How did you find out about Legacy of the Realm? | Multi-select | Social media / Friend referral / LARP forum / Reenactment event / Press article / Influencer / Search engine / Other | YES | Marketing channel attribution |
| 13 | Rate the following aspects (1–10 each): Quest system / Economy system / Tournament/combat / Music & atmosphere / Tavern experience / Guild workshops / Staff helpfulness / Costume standards / Camp facilities / Sanitation | Matrix (10 sub-questions) | 1–10 each | YES | Detailed component analysis |
| 14 | Did you participate in any of the following? (check all): Quests / Guild workshop / Tournament / Political RP / Gambling / Tavern evening / Craft purchase / Shadow economy | Multi-select | Checkbox list | YES | Engagement breadth measurement |
| 15 | Any other comments, stories, or feedback? | Open text | Free text | No | Rich qualitative data. Often contains the most valuable insights. |

Target survey response rate: 50%+ of attendees. Offer an incentive: ‘Complete the survey and receive a 10% early bird discount on next year’s ticket.’

## 2D. Year-Over-Year Comparison Framework

After Year 1, every metric is compared against the previous year. This reveals trends, validates improvements, and exposes emerging problems.

| Metric Category | Year-Over-Year Question | Healthy Trend | Warning Trend | Action If Warning |
| --- | --- | --- | --- | --- |
| Attendance | Is total attendance growing? | +15–25% per year until capacity | Flat or declining | Review marketing, pricing, timing, competition. Conduct lapsed-attendee survey. |
| Satisfaction | Is overall satisfaction improving? | +0.3–0.5 points per year on 10-point scale | Flat or declining | Deep-dive into component scores. Identify which area dragged down. Fix it. |
| NPS | Are more people recommending us? | NPS increasing by 5–10 points per year | NPS declining | Analyze detractor feedback. Address root causes. Consider experience overhaul. |
| Return rate | Are people actually coming back? | Actual return rate matches or exceeds stated intent from previous year | Actual return < stated intent by >15 points | Gap = barriers (price, dates, logistics) not experience. Survey lapsed. Offer incentives. |
| Revenue per head | Are we earning more per participant? | Growing with premium offerings and upsells | Flat or declining despite price increases | Value perception declining. Add value before adding price. |
| Economy health | Is the token economy stable and engaging? | Velocity stable. Redemption rate stable or declining. No inflation events. | Velocity spiking. Redemption rate increasing. Merchant price complaints. | Review money supply, sinks, and pricing. Activate inflation controls. See Economy Database. |
| Safety | Are incidents decreasing? | Fewer incidents per 100 participants each year | Incidents per capita increasing | Review safety protocols, training, equipment. Consider activity restrictions. |
| Staff satisfaction | Are staff and volunteers happy? | Satisfaction stable or improving. Volunteer return rate >60%. | Satisfaction declining. Key volunteers not returning. | Staff burnout, under-appreciation, or structural problems. Debrief deeply. Invest in staff welfare. |
| Quest engagement | Are quests being completed and enjoyed? | Completion rate stable. Variety increasing. Survey ratings improving. | Completion rate declining. Same quest types repeated. Survey complaints. | Quest fatigue. Need new quest types, better story arcs, more variety. Invest in Quest Lead resources. |
| Immersion score | Is the world getting MORE real? | Immersion rating improving by 0.3–0.5/year | Flat or declining immersion rating | Identify what breaks immersion (survey Q11). Invest in costume standards, soundscape, NPC quality, prop quality. |
| Cost efficiency | Are we spending smarter? | Net margin improving while quality stable or improving | Costs growing faster than revenue | Audit every cost category. Identify waste. Renegotiate supplier contracts. Don’t cut quality — cut waste. |

## 2E. Analytics Report Template

The post-event analytics report follows this structure. It is presented to the core team 6 weeks after each event.

| Section | Content | Length | Owner |
| --- | --- | --- | --- |
| Executive Summary | 3–5 key findings. Headline numbers. Overall health assessment. | 1 page | Analytics Lead |
| Attendance & Demographics | Total attendance, show rate, class distribution, new vs. returning, geographic origin, language distribution. | 1–2 pages with charts | Community Director |
| Satisfaction Deep-Dive | Survey results: overall, immersion, food, value, safety, NPS. Component matrix breakdown. Top positives and negatives (coded themes). | 2–3 pages with charts | Community Director |
| Financial Performance | Revenue vs. budget by line. Cost vs. budget by line. Margin. Token economy audit: velocity, redemption, inflation metrics. | 2–3 pages with tables | Economy Director / Finance Lead |
| Operational Review | Safety incident summary. Permit compliance. Waste management. Staffing performance. Volunteer return intent. | 1–2 pages | Operations Director |
| Content & Immersion Review | Quest completion rates by type. Titles granted. Guilds chartered. Settlements named. Story arc outcomes. NPC performance notes. | 1–2 pages | Immersion Director |
| Marketing & CRM Review | Channel attribution. Email engagement. Conversion funnel. CRM stage movement. Social media metrics. | 1–2 pages | Community Director |
| Partnership Review | Active partnerships performance. New partnerships identified. Partnership satisfaction ratings. | 1 page | Relationship owners (compiled by Community Director) |
| Year-Over-Year Comparison | Every KPI vs. previous year. Trend arrows. Highlight improvements and regressions. | 1–2 pages (from Y1 onward) | Analytics Lead |
| Recommendations | Top 10 prioritized recommendations for next year. Each with: problem identified, proposed solution, estimated cost, owner, deadline. | 1–2 pages | Core team (collaborative) |
| Appendices | Raw survey data. Financial spreadsheets. Incident reports. Quest completion logs. | As needed | Various |

Total report length: 12–20 pages + appendices. This is a WORKING DOCUMENT, not a vanity piece. Every page must contain actionable information.

## 2F. Continuous Improvement Cycle

Analytics are worthless unless they drive change. This cycle ensures every finding becomes an action.

| Step | When | Action | Output | Who |
| --- | --- | --- | --- | --- |
| 1. Collect | During event + 2 weeks post | Gather all data per timeline (2A) | Raw data in Airtable, survey responses, financial records | All departments |
| 2. Analyze | Weeks 2–5 post-event | Process data, calculate KPIs, code qualitative feedback, generate charts | Draft analytics report | Analytics Lead + department heads |
| 3. Present | Week 6 post-event | Present report to full core team. Discuss findings. Challenge interpretations. | Validated findings. Shared understanding. | Analytics Lead presents; all attend |
| 4. Prioritize | Week 6–7 post-event | From findings, identify top 10 improvements. Score by impact and feasibility. Assign owners. | Prioritized improvement list with owners and deadlines | Sovereign + core team |
| 5. Plan | Weeks 7–10 post-event | Improvement owners draft implementation plans. Budget allocated. Timeline set. | Implementation plans per improvement | Improvement owners |
| 6. Execute | Months 3–12 post-event (pre-production for next year) | Implement improvements during pre-production for the next event | Improvements built into next year’s systems, schedule, design | All departments |
| 7. Verify | During next event | Monitor whether improvements worked. Collect same KPIs. Compare. | Year-over-year comparison confirms or denies improvement | Analytics Lead |
| 8. Repeat | After next event | Full cycle again. Every year, the Realm gets measurably better. | Continuous compounding improvement | Everyone |

The Realm that measures, learns. The Realm that learns, improves. The Realm that improves, endures.

THE LEGACY OF THE REALM OPERATIONAL LIBRARY IS COMPLETE

10 Documents | 15,000+ Paragraphs | Every System Defined

1. Master Blueprint v2.0 — The Bible

2. Guild & Profession Database — 18 guilds, 150+ supplier entries, MVP strategy

3. Core Systems Database — Classes, quests, zones, staffing roles

4. Economy & Supplier Database — Currency, 200+ items, 3 economy models, procurement

5. Risk Playbook & Legal Bible — 30 risks, 7 protocols, full French compliance

6. Costume & Asset Inventory — Wardrobe specs, lending library, €38K asset register

7. Lore Bible & Communication Database — World history, NPCs, all scripts and templates

8. Food & Atmosphere Database — 8-day menu, HACCP, soundscape, music programming

9. Operations Trilogy — 10-day schedule, participant CRM, weather contingency

10. Partnerships & Analytics — Sponsor pipeline, post-event measurement, continuous improvement

The foundations are laid. The systems are designed. The world is written.

Now it is time to build.

A Realm to Enter, A Legacy to Forge.